Local Cigarette Tax Enforcement Study (HB 2038 and SB 1085)

Work Plan

| Action | Target Date | Completion Date |
| --- | --- | --- |
| Compile background information | April 13, 2011 |  |
| Interested Parties Meeting – Clarify Purpose of Working Group, Identify Issues, etc. | April 20, 2011 |  |
| Compile list of issues identified at Interested Parties meeting | April 29, 2011 |  |
| Information/Comments from Interested Parties due | May 24, 2011 |  |
| Interested Parties Meeting #2 – Possible Site Tour | July 8, 2011 |  |
| Information/Comments from Interested Parties due | July 29, 2011 |  |
| Draft Report to Interested Parties for Comment | September 7, 2011 |  |
| Interested Parties Meeting #3 – Discuss Report | September 30, 2011 |  |
| Interested Parties Comments due | September 30, 2011 |  |
| Final Draft to Interested Parties for Comments included in Final Report to GA | October 21, 2011 |  |
| Interested Parties Comments included in Final Report due | November 18, 2011 |  |
| Final Report to GA | December 1, 2011 |  |